## Schedules
Schedule - List - PROJECT NAME / ADDRESS (Kairos Legacy Homes)
ID # | Title | Complete | Duration | Start | End
1 | 001- Architectural | FALSE | 2
2 | 002- Engineering Design / Load Calcs | FALSE | 2
3 | 003- Survey - Lot grading Plan and Topo | FALSE | 5
4 | 004- Print Plans and get stamp with Enginner | FALSE | 1
5 | 005- Permits | FALSE | 30
6 | 020- Utilities - Request Electrical Connection | FALSE | 1
7 | 021- Utilities - Request Water Connection | FALSE | 1
8 | 031- Boundary Stake Out | FALSE | 1
9 | 032- Cleaning Lot | FALSE | 2
10 | 033- Rough Stake Out | FALSE | 1
11 | 034- Fill Dirt / Pad | FALSE | 2
12 | 035- House Stake Out | FALSE | 1
13 | 040- Portable Toilet | FALSE | 1
14 | 050- Prepair the rail | FALSE | 1
15 | 051- Compaction test | FALSE | 1
16 | 052- Plumbing, Electrical & Mech Underground | FALSE | 1
17 | 053- Sewer Connection - Utility Water Company | FALSE | 1
18 | 054- Underground Inspection | FALSE | 1
19 | 056- Water line inspection | FALSE | 1
20 | 057- Sewer Tap Inspection | FALSE | 1
21 | 060- Prepair Slab | FALSE | 1
22 | 070- Slab Inspection | FALSE | 2
23 | 071- Driveway Preliminary Inspection | FALSE | 1
24 | 072- Pouring Slab | FALSE | 1
25 | 075- Dumpster Delivery | FALSE | 1
26 | 080- Exterior Masonry | FALSE | 2
27 | 216- Water Meter Set up | FALSE | 1
28 | 085- Truss Layout | FALSE | 1
29 | 090- Lintel Inspection | FALSE | 1
30 | 091- Meter Can Installation | FALSE | 1
31 | 092- Pouring Lintels | FALSE | 1
32 | 093- TUG Inspection | FALSE | 1
33 | 094- Stucco Grading | FALSE | 1
34 | 100- Prepair Trusses to Fly | FALSE | 1
35 | 101- Framing | FALSE | 4
36 | 102- Sheathing | FALSE | 2
37 | 103- Exterior Doors | FALSE | 1
38 | 104- Install Windows | FALSE | 1
39 | 105- Plumbing Rough In | FALSE | 1
40 | 110- Sheathing Inspection | FALSE | 1
41 | 111- Apply Underlayment | FALSE | 1
42 | 112- Wall Sheathing / Sub-siding Inspection | FALSE | 1
43 | 113- 2º Plumbing Rough In Inspection | FALSE | 1
44 | 114- HVAC Rough In | FALSE | 2
45 | 115- Electrical Rough-In | FALSE | 1
46 | 120- Dry in flash Inspection | FALSE | 1
47 | 121- HVAC Rough in Inspection | FALSE | 1
48 | 135- Electrical Rough in Inspection | FALSE | 1
49 | 130- Install Shingles | FALSE | 1
50 | 140- Framing / Combined Inspection | FALSE | 2
51 | 150- Lathe | FALSE | 1
52 | 151- Lathe Inspection | FALSE | 1
53 | 155- Insulation Install | FALSE | 1
54 | 156- Insullation Inspection | FALSE | 1
55 | 170- Stucco | FALSE | 1
56 | 175- Drywall | FALSE | 6
57 | 180- Septic Tank Installation | FALSE | 7
58 | 181- Hook up | FALSE | 1
59 | 182- Hook up Inspection - Septic | FALSE | 1
60 | 183- DOH (Septic) Inspection | FALSE | 1
61 | 200- Painting-Exterior | FALSE | 1
62 | 201- Painting-Interior | FALSE | 1
63 | 205- Garage Door Installation | FALSE | 1
64 | 210- Clean / Prime Flooring and Wet Walls | FALSE | 1
65 | 211- Tile Flooring - Bathroom - Installation | FALSE | 1
66 | 212- Tile Flooring Grout | FALSE | 1
67 | 213- Tile Wall (Bathrooms) | FALSE | 1
68 | 215- Well Installation | FALSE | 1
69 | 220- Soffit | FALSE | 1
70 | 221- Soffit - Inspection | FALSE | 1
71 | 225- Tile Wall Grout (Bathrooms) | FALSE | 1
72 | 230- Tile / Vinyl - Other rooms - Installation | FALSE | 2
73 | 250- Cabinet Install | FALSE | 1
74 | 255- HVAC Finish | FALSE | 1
75 | 260- Light Fixture Install | FALSE | 2
76 | 265- Driveway Cut / Install Culvert Pipe | FALSE | 1
77 | 266- Driveway Formboard | FALSE | 1
78 | 270- Countertop Install | FALSE | 1
79 | 280- Driveway - Pre-Pour Inspection | FALSE | 1
80 | 281- Door, Baseboards and Casings | FALSE | 1
81 | 285- Plumbing Fixtures Install | FALSE | 1
82 | 290- Mirrors / Blinds / Shelves / Numbers | FALSE | 1
83 | 300- Driveway - Pouring | FALSE | 1
84 | 301- Pre-Power Inspection | FALSE | 1
85 | 305- Water Hook up - Meter or Well | FALSE | 1
86 | 310- Remove Dumpster from site | FALSE | 1
87 | 311- Remove Portable Toilet | FALSE | 1
88 | 315- Final Grading | FALSE | 1
89 | 316- Asphalt Repair | FALSE | 1
90 | 330- Site Drainage Inspection | FALSE | 2
91 | 335- Install Mailbox | FALSE | 1
92 | 338- Install Clean Out Pad | FALSE | 1
93 | 340- Electrical Meter Set up | FALSE | 1
94 | 341- Electrical Starting | FALSE | 1
95 | 342- Sod | FALSE | 1
96 | 345- Blown Door Test | FALSE | 1
97 | 350- HVAC Starting | FALSE | 2
98 | 400- Termite Bait | FALSE | 1
99 | 410- Utility Inspection - Final Building | FALSE | 1
100 | 415- Blown Insulation | FALSE | 1
101 | 420- Rough Punchout | FALSE | 1
102 | 455- Driveway - Final Inspection | FALSE | 1
103 | 460- Painting/Caulking - Door/Baseboards/Casings | FALSE | 2
104 | 461- Final Painting | FALSE | 2
105 | 462- Painting Front Door | FALSE | 1
106 | 470- Door Knobs and Door Stop | FALSE | 1
107 | 475- Final Cleaning | FALSE | 1
108 | 480- Appliance Installation | FALSE | 1
109 | 500- Electrical Final Inspection | FALSE | 1
110 | 501- Mechanical Final Inspection | FALSE | 1
111 | 502- Plumbing Final Inspection | FALSE | 1
112 | 505- Building Final Inspection | FALSE | 2